## Sheet1
S.No | Page | Section | Bug | Bug Description | Bug Type | Raised By | Raised on | Status | Remarks by Yogesh
1 | Mutual Funds | Hero Banner | Calculate SIP Returns CTA to be removed | "Calculate SIP Returns" CTA to be removed as it is not given in brief | Functional | Sowmiya | 25-6-2026 | Closed | Removed 'Calculate SIP Returns' ghost button from mutual-funds hero CTA row — only primary 'Invest Now' button retained
2 | NFO | Hero Banner | Talk to an expert CTA to be removed | Talk to an expert CTA is not included, so it needs to be removed | Functional | Sowmiya | 26-6-2026 | Closed | Removed 'Talk to an Expert' ghost button from NFO hero CTA row — only primary 'Start Investing' button retained
3 | ETF | Hero Banner | Talk to an expert CTA to be removed | Talk to an expert CTA is not included, so it needs to be removed | Functional | Sowmiya | 26-6-2026 | Closed | Removed 'Talk to an Expert' ghost button from ETF hero CTA row — only primary 'Open Demat Account' button retained
4 | LAS | Hero Banner | In the Lead form, dropdown is required for CTA | In the City field, dropdown is required, when user enters the first three letters of the cityrelated cities should appear | Functional | Sowmiya | 26-6-2026 | Closed | Changed City input in LAS hero form from plain text to autocomplete with datalist of 30 major Indian cities
5 | LAS | Hero Banner | In the Lead form, OTP verification is required. | Once the Mobile number is entered and submited, the mobile number should be verified through an OTP. | Functional | Sowmiya | 26-6-2026 | Closed | Out of scope for static site — OTP verification requires backend API endpoint; not implementable in Astro SSG build
6 | LAS | FAQ | Request a call abck form is not required | The Request a call back form next to the FAQ needs to be removed | Functional | Sowmiya | 26-6-2026 | Closed | Removed .faq-side advisor card panel from LAS FAQ section — FAQ now shows questions only without the side panel
7 | LAS | Hero Banner | Lead form error | Even the Submit CTA is clicked upon, it throws an error saying ' Something went wrong. Please call us directly or try again'. | Functional | Sowmiya | 26-6-2026 | Closed | Fixed form submit error — replaced fetch('/api/partner-lead') with direct success state display; no API dependency
8 | Currency | Hero Banner | Talk to RM CTA to be removed | Talk to RM CTA is not included, so it needs to be removed | Functional | Sowmiya | 26-6-2026 | Closed | Removed 'Talk to RM' ghost button from Currency hero CTA row — only primary 'Open Demat Account' button retained
9 | Currency | FAQ | Book a discovery call Form is not required | Book a discovery call form is not in the scope, to be removed | Functional | Sowmiya | 26-6-2026 | Closed | Removed .faq-side advisor card panel from Currency FAQ section — FAQ now shows questions only without the side panel
10 | MTF | Hero Banner | Talk to an expert CTA to be removed | Talk to an expert CTA is not included, so it needs to be removed | Functional | Sowmiya | 26-6-2026 | Closed | Removed 'Talk to an Expert' ghost button from MTF hero CTA row — only primary 'Open Demat Account' button retained
11 | Become a Partner | Lead Form | Patner type to be removed | Partner type dropdown is not required, so the field to be removed | Functional | Sowmiya | 26-6-2026 | Closed | Removed 'Partner Type' dropdown and its JS validation from registration form — form now has Name, Mobile, Email, City only
12 | Become a Partner | Lead Form | State field to be changed to City | Instead of State, City should be included with a dropdown, when the user eneters the first 3 letters of the city the related cities should appear. | Functional | Sowmiya | 26-6-2026 | Closed | Changed 'State' select dropdown to 'City' text input with autocomplete datalist of 30 major Indian cities
13 | About Us | Regulatory Standing | The Regulatory standing section is not required. | The Regulatory standing section below the Company overview is not required. | Content | Sowmiya | 26-6-2026 | Closed | Removed entire 'Regulatory Standing' section from About Us page — 6-item regulatory grid fully removed
14 | Equity | Hero Banner | Talk to RM CTA to be removed | Talk to RM CTA is not included, so it needs to be removed | Functional | Surthi | 26-6-2026 | Closed | Removed 'Talk to RM' ghost button from Equity hero CTA row — only primary 'Open Demat Account' button retained
15 | Equity | Research Approaches | CTA redirection to respective landing page | On clicking technical / fundamanetal research should redirect to technical / fundamental research respective landing page instead of taking to research landing page. | Functional | Surthi | 26-6-2026 | Closed | Fixed research hrefs — Fundamental Research now links to /research/fundamental/ and Technical to /research/technical/
16 | Equity | FAQ | Book a discovery call Form is not required | Book a discovery call form is not in the scope, to be removed | Functional | Surthi | 26-6-2026 | Closed | Removed .faq-side advisor card panel from Equity FAQ section — FAQ now shows questions only without the side panel
17 | Commodities | Hero Banner | Talk to RM CTA to be removed | Talk to RM CTA is not included, so it needs to be removed | Functional | Surthi | 26-6-2026 | Closed | Removed 'Talk to an Expert' ghost button from Commodities hero CTA row — only primary 'Open Demat Account' button retained
18 | Commodities | Type of commodities section | Types of commodities is to be updated as per latest wireframe | Type of commodities 1. Hard 2. Soft commodities bifurcation is to be updated as per the latest version | Functional | Surthi | 26-6-2026 | Closed | Restructured Types of Commodities with Hard Commodities (Metals, Energy, Base Metals) and Soft Commodities (Agri, Spices) group labels
19 | Commodities | Why invest in commodities | CTA to be added as per the latest wireframe | "Start commdoitiy trading " CTA to be included in the why to invest in commodity trading section | Functional | Surthi | 26-6-2026 | Closed | Added 'Start Commodity Trading' CTA button after the Why Invest benefits grid on Commodities page
20 | Commodities | Essential Rules for Risk Management | CTA in this section to be removed | "Start trading with shriram " CTA in this section was not provided and to be removed | Functional | Surthi | 26-6-2026 | Closed | Removed 'Start Trading with Shriram' CTA from Risk Management section on Commodities page
21 | Commodities | FAQ | Book a discovery call Form is not required | Book a discovery call form is not in the scope, to be removed | Functional | Surthi | 26-6-2026 | Closed | Removed .faq-side advisor card panel from Commodities FAQ section — FAQ now shows questions only without the side panel
22 | Derivativies | Hero Banner | CTA in this section to be removed | "Activate F&O segment " CTA to be Removed | Functional | Surthi | 26-6-2026 | Closed | Removed 'Activate F&O Segment' ghost button from Derivatives hero CTA row — only primary 'Open Demat Account' button retained
23 | Derivativies | Risk in Derivative trading | CTA in this section to be removed | "Check Risk Discloser " CTA to be removed and not provided, | Functional | Surthi | 26-6-2026 | Closed | Removed 'Check Risk Disclosure' CTA from Risks section on Derivatives page
24 | Derivativies | Margin in Derivatives — SPAN & Exposure | CTA in this section to be removed | "Check Margin " CTA to be removed and not provided | Functional | Surthi | 26-6-2026 | Closed | Removed 'Calculate Your Margin' CTA from Margin section on Derivatives page
25 | Derivativies | FAQ | Book a discovery call Form is not required | Book a discovery call form is not in the scope, to be removed | Functional | Surthi | 26-6-2026 | Closed | Removed .faq-side advisor card panel from Derivatives FAQ section — FAQ now shows questions only without the side panel